## 00_Final_JP
区分 | 本日決めたこと | 詳細
今日の結論 | ACTIVEは最大2件だけ | BUG-003 と BUG-004+291 を次に現場Claudeへ渡す。他のP1候補は一括ACTIVE化しない。
最優先の事故防止 | 公開状態と候補消失 | 公開状態が勝手に変わる疑い、候補が見えずに消える問題、YOSHILOVER対象外メールが来る問題を最優先で見る。
品質方針 | ハルシネーション防止 | AI/Codexに足りない数字・勝敗・選手名を書かせない。source/meta由来の事実だけでテンプレに入れる。
コスト方針 | Geminiを呼ばない設計 | 品質改善と同時にGemini追加呼び出し、再生成、メール増加を抑える。まずregex/marker/template/slot-fillで対処する。
マーケ方針 | 巨人専門価値 | 二軍・若手・復帰組・スタメンを追える、のもとけ型の巨人専門サイトに寄せる。ただしsource追加は後。
運用方針 | userは貼るだけ | userは違和感や現場報告をチャットに貼るだけ。CodexがBUG_INBOXへ整理し、ClaudeがACTIVE最大2件を進める。
次ACTIVE候補 | GCP Codex WP本文修正プレビュー v0 | 本文品質を早く見るためのpreview-only候補。Gemini原則0、WP本文変更なし。BUG-004+291後、またはBUG-003と入れ替え検討。

## 01_ACTIVE_Detail
ID | ????? | ??? | ?? | ????? | ?????? | close?? | ??/??
BUG-004+291 | publish=0???? + narrow publish-path unlock | P1 | ACTIVE 1??? | ???????????user??????????????????????????????????publish path????????? | read-only?publish=0??????277/289/290/4-tier/duplicate/backlog/freshness/body_contract/subtype/numeric/placeholder/source facts?????????unlock??????????????292 body_contract_fail durable ledger????????? | ?????(YOSHILOVER???source_url?subtype/template_key high confidence?numeric/body pass?placeholder???silent skip???title???review/hold????)????????publish????????????body_contract_fail???????????ledger/log????? | publish gate?????postgame strict/stale/duplicate??????noindex???review threshold?????mail?????ticket???292??ACTIVE?????
282-COST | flag ON? preflight active rejection?? | OBSERVE | OBSERVE | 282?flag ON??????????????????????????? | preflight active rejection?????silent skip?Gemini??mail storm????? | ????????????????????????? | ?????env remove?user?????????
298-Phase3 | 5/3 19:35 JST 24h gate?? | OBSERVE | OBSERVE | 24h gate?PASS/FAIL?????? | 5/3 19:35 JST???? | PASS/FAIL/rollback??????? | ????????????
245 | WP plugin upload | USER_DECISION_REQUIRED | user???? | WP admin upload?????????????user??? | upload????OK/HOLD/REJECT???? | user?OK????????? | publish=0?????????

## 02_KEEP_Detail
ID | テーマ | 扱い | 詳しい理由 | 次の扱い
229 / 282 / 293 | Gemini費用削減本線 | KEEP | Gemini費用削減はまだ本線。282は293のFULL_EXERCISE_OK後に進める。preflight gate、skip visible化、重複抑制を中心に、Geminiを呼ばない設計へ寄せる。 | 293のexercise evidence確認、282 flag ONはuser判断境界。コスト削減と候補可視化を両立する。
234 / 247 / 250 / 256 | 本文テンプレ・strict系 | KEEP | ハルシネーション対策の本線。優先順は postgame strict → farm_result → lineup → 監督/選手コメント。コメント系は全文がなくても一部引用ならよいが、重複通知を抑える。 | source/meta由来のslot-fillとbody validatorで守る。自由作文で補完させない。
247 | postgame strict | KEEP | 一軍試合後記事では、特に先発投手成績を守る。勝敗・スコア・投手成績の誤りはブランド毀損が大きい。 | 先発投手成績、勝敗、得点場面、スコアをsource/meta由来に限定。
254 | 投手回数・スターター表記正規化 | KEEP | 数字・投手成績のハルシネーション防止に直結。1/3回、2/3回、先発/リリーフ表記の誤読を防ぐ。 | numeric guard / baseball fact consistencyへ吸収または連動。
264 | 今後の重複記事削減 | ABSORB | 過去重複記事cleanupは不要。ただし今後の重複記事を減らすのは急ぎ。 | 229 / 235 / 300 / BUG-004へ吸収。cleanup mutationはしない。
277 / 278 / 279 / 280 | タイトル・RTタイトル・メール件名・summary改善 | KEEP | 最優先は「何の記事かわからない」タイトルの解消。SEOや煽りより、読者が一瞬で内容を理解できることを優先。 | まずタイトルclarityを改善。メール件名/summaryは後続。SEOは後で対策。
281 | 二軍・若手・復帰組を増やす | KEEP | YOSHILOVERの差別化軸。大手が出さない巨人専門情報、のもとけ型の価値。最初は復帰組と二軍スタメンを重視。 | source追加は後。まず既存source/既存テンプレで増やせる範囲を確認。
283 | 独自記事要件・regression contract | KEEP | 独自記事や観戦ガイドへ広げる前に、どの品質条件を満たすべきかを契約化する。 | 実装前にregression contractとして保持。
290 | weak title rescue | KEEP | 弱いタイトル救済は必要。ただし自動修正より検知優先。 | 弱いタイトルを検知し、候補化/review化してから段階的に修正。
295 | subtype誤分類防止 | KEEP / P1候補 | ハルシネーション防止で重要。最優先はcomment系がpostgame扱いになる事故。加えて勝敗・スコア・試合結果factの誤分類も防ぐ。 | 234/247と連動し、template_key判定はconfidence highのみ。判定不能はdefault/review。
294 | release composition gate | KEEP | 止めているticketのコードや作業ゴミがbuild/deployに混ざる事故を防ぐ親ticket。 | deploy前にcommit range、HOLD ticket混入、rollback target 3種を確認する。
195 / 197 | 記事下Xシェア導線 | KEEP | 読者向けの手動Xシェア導線は必要。X APIや自動投稿ではなく、読者が共有しやすい導線。 | front改善候補として保持。
245 | 自動投稿カテゴリ非表示 | KEEP / 次front候補 | 画面上に「自動投稿」カテゴリがまだ見える。読者に内部カテゴリが見えるのは不自然。 | 次front候補。表示修正・確認を行う。
246-MKT | 今日の巨人ファン観戦ガイド | KEEP | トップページで今日見る順番が分かる観戦ガイド。記事一覧ではなく、試合前後の導線を作る。 | まずトップページだけ。記事下展開は後。
299 / 201 / 275 | pytest / CI / flaky整理 | KEEP親 / 吸収 | pytest/CI/flaky整理は必要。299を親にし、201と275は吸収/close候補。GitHub Actions赤は現状出ていない。 | 299でbaseline/new failure/out-of-scopeの表現を統一。

## 03_HOLD_OBSOLETE
ID | テーマ | 扱い | 理由
230 / 230A / 230A1 / 230D | GCP runtime cost / scheduler cadence / overlap audit | HOLD | 後で。安全な小額cleanupは候補として残すが、今の主線ではない。Artifact Registry等は安全なら検討。
238 | night draft-only / morning report | OBSOLETE候補 | user回答で捨てる。夜間draft-only/朝レポートは今後の主線から外す。
248 / 255 / 260 | マーケ拡張・コメントbadge・独自記事型 | HOLD | 後回し。246-MKT観戦ガイドが先。
251 | SEO/noindex戦略 | DONE/OBSOLETE候補 | SEOはいじらない。もうできている。今後ACTIVEに上げない。
252 | X自動化/関連施策 | OBSOLETE候補 | X文面はGPTsで作るため不要寄り。
274 | Gmail filter | OBSOLETE候補 | Gmail通知仕分けは不要。GitHub Actions赤の根本対応でもない。
288 / 210 / 210b / 210e | source expansion系 | HOLD / 288へ吸収 | source追加・取得元拡張は後で。210系は288に吸収。
296 | codex-shadow redesign | OBSOLETE候補 | codex-shadow再設計は不要。

## 04_Rules_Detail
ルール | 内容
チケット番号 | 振り直し禁止。既存番号は履歴として残し、必要ならalias/吸収先を付ける。
ACTIVE数 | 最大2件。今はBUG-003とBUG-004+291。
user入力 | userはチャットに違和感や現場報告を貼るだけ。Excel編集や優先度分類はしない。
Codex役割 | 貼られた報告をBUG_INBOXへ反映し、既存ticketへ吸収し、ACTIVE候補を最大2件に圧縮する。
Claude役割 | 現場管理。ACTIVE最大2件を実行管理し、Codex A/Bへdispatchする。正常系の長い報告はしない。
コスト横串 | Gemini追加呼び出しを増やさない。重複再生成を減らす。メール通知を増やさない。
ハルシネーション対策 | 数字・勝敗・選手名・投手成績はsource/meta由来に限定。足りないものをAIに書かせない。
292通知 | body_contract failは通常メール不要。ledger/logで件数確認できればよい。
291通知 | YOSHILOVER対象外sourceメールは完全に送らない。mail対象ならpublish判定へ戻すが、境界はread-only auditで確認。
DONE条件 | evidenceがあるものだけDONE。証拠なしはP1_REVIEW/OBSERVE継続。

## 05_Claude_Prompt
項目 | 内容
現場Claudeへ渡す1文 | BUG_INBOX初回棚卸しでは、ACTIVE候補は BUG-003 WP status mutation audit と BUG-004+291 silent skip / 候補消失 / YOSHILOVER対象外メール / 自動公開判定整理の2件だけです。他のP1候補は一括ACTIVE化しないでください。291は対象外sourceメールを完全に送らない方針、mail対象ならpublish判定へ戻す方針ですが、publish判定境界が曖昧なのでまずread-only auditで確認してください。292は通常メール不要、ledger/log確認に寄せてください。
禁止 | 新規deploy、env/flag変更、Scheduler変更、SEO変更、source追加、Gemini call増加、mail通知増加はこの棚卸し作業ではしない。
報告してよいもの | ACTIVE完了、P1相当の異常、rollback必要、USER_DECISION_REQUIRED、新たにP0/P1へ昇格すべき証拠。
報告しないもの | cycle silent、異常なし定期報告、次wake予定、monitorなし、HOLD/OBSERVE/DONEの正常報告、長いlog貼り付け。
????????? | BUG-004+291 ??? publish=0???? + narrow publish-path unlock ????????????ticket?????????????publish gate?????????????????????read-only??????????????????publish path?????????????????: 277 title quality?289 post_gen_validate?290 weak title rescue???4-tier??strict?duplicate/backlog/freshness?body_contract?subtype misclassify?numeric guard?placeholder?source facts???publish??????????: YOSHILOVER???source_url???subtype/template_key high confidence?numeric guard pass?body_contract pass?placeholder???silent skip???title?????????????review/hold???????????: publish gate??????????????????????noindex???review threshold???????mail???user?????SEO?????trigger????????narrow unlock?????P1???rollback???USER_DECISION_REQUIRED??????????????
2026-05-03 ??Claude?????? | ?????????Claude?BUG-004+291???????????????publish=0???? + narrow publish-path unlock??BUG-004+291??????????????????????292 body_contract_fail durable ledger?????ACTIVE?????BUG-004+291????????????????????????ACTIVE?BUG-004+291???OBSERVE?282-COST?298-Phase3?USER_DECISION_REQUIRED?245 WP plugin upload???publish gate?????postgame strict/stale/duplicate??????noindex???review threshold???????mail????????????body_contract_fail???????????????read-only?publish=0??????????unlock???????????????????

## 06_NewCandidate_GCP_Codex
項目 | 内容
候補名 | GCP Codex WP本文修正プレビュー v0
扱い | NEW_CANDIDATE。ただしuser希望により次ACTIVE候補へ昇格可能。
目的 | WordPress本文をいきなり変更せず、GCP Codexで修正文候補だけ作り、userが早く品質を確認できるようにする。
なぜ重要か | 本文品質が運用負担の中心。完全自動化前に、GCP Codexがどの程度安全に本文を直せるか早く見たい。
対象 | まず postgame または farm_result の少数。最初から全subtypeに広げない。
必須制約 | preview-only / WP本文変更なし / publish状態変更なし / env/flag/Scheduler/SEO/source変更なし。
コスト制約 | Gemini call原則0。使う場合は別判断・上限付き。まずGCP Codex/deterministic template/source-meta slot-fillで行う。
本文修正方針 | 自由作文ではなく、source/metaにある数字・勝敗・選手名・投手成績だけをテンプレに入れる。足りない事実は補完しない。
やってよい修正 | placeholder削除、空見出し削除、sourceにないoptional section削除、短文化、タイトルと本文の整合確認、元本文/修正文diff生成。
やってはいけない修正 | sourceにない数字/選手名/勝敗/コメントの補完、X投稿文生成、長文再作文、Gemini追加呼び出し前提の修正。
出力 | 元本文、修正文候補、変更理由、削ったsection、source/meta由来fact一覧、危険/不明点をledgerまたはreview artifactへ出す。
close条件 | userが元本文と修正文候補を比較できる。数字・勝敗・選手名のハルシネーションなし。費用増なし、または小さい。
ACTIVE化条件 | BUG-004+291の整理後、または本文品質確認を優先する場合に、BUG-003と入れ替えてACTIVE候補へ昇格可能。
関連ticket | 247 postgame strict / 234 template contract / 295 subtype誤分類 / 290 weak title rescue / 254 numeric normalization
現場Claudeへ渡す時の注意 | いきなり本番本文を書き換えない。preview-onlyで品質を見る。Gemini制限を明記。

## 00_UserReview
?? | ?? | ????
ACTIVE?? | BUG-003 / BUG-004+291 | WP status mutation audit ? silent skip/????/??????/?????????2??
????? | 229 / 282 / 293 | ?????282 flag ON?293 FULL_EXERCISE??
?????? | 234 / 247 / 250 / 256 / 254 / 283 | ???postgame strict?farm_result?lineup?quote????
?????? | 277-280 / 290 | ??????????????????????????/???
?????? | 281 | ??????????????????????????
front/MKT | 245 / 195/197 / 246 | ???????????????X????????????????
HOLD/??? | 230? / 248 / 255 / 260 / 288 | runtime cost???????source?????
OBSOLETE?? | 238 / 252 / 274 / 296 | ??draft-only?X??????Gmail filter?codex-shadow redesign??????
CI?? | 299? / 201 / 275 | ???299?????201/275???/close???
Final hearing | Round6???? | 295?comment?postgame??????/?????????????291?publishable??OK???????292?ledger/log?????????????
Cost principle | ???? | ????????Gemini?????/??????/????????????????????source/meta??????template/regex/slot-fill???

## 01_AllTickets
num | ticket | folder | status | priority | title | proposed_bucket | reason | next_action | user_review | path
229 | 229-gemini-cost-governor-and-llm-call-reduction | doc/active | REVIEW_NEEDED | P0.5 | 229 Gemini cost governor + LLM call reduction | KEEP? | Gemini????????229/282/293????? | 282?293 FULL_EXERCISE? | ANSWERED | doc/active/229-gemini-cost-governor-and-llm-call-reduction.md
245 | 245-front-hide-auto-post-category-label | doc/active | READY | P0.5 | 245 front hide internal auto-post category label | KEEP/次front候補 | user確認: 画面上に「自動投稿」がまだ見える。DONE不可。 | front表示修正またはdeploy/表示確認へ | ANSWERED | doc/active/245-front-hide-auto-post-category-label.md
246 | 246 | doc/active | READY | P2 | viral topic detection (SNS バズ検出 → 既存 subtype routing、dry-run) | KEEP | user回答: 今日の巨人ファン観戦ガイドはやりたい。 | MKT本線として保持 | ANSWERED | doc/active/246-viral-topic-detection.md
247 | 247-QA | doc/active | READY | P0.5 | postgame strict slot-fill POC(LLM 自由作文 → JSON 抽出 + 固定 template に slot-fill、type 別 block 振り分け) | KEEP | ??????/strict????????postgame strict?farm_result?lineup?quote? | ??????????? | ANSWERED | doc/active/247-QA-postgame-strict-slot-fill-poc.md
248 | 248-MKT-2 | doc/active | READY | P1 | single 記事下部「この試合の関連記事」(同 game 導線、PHP front-only narrow) | HOLD | user回答: マーケ拡張は後回し。 | 246後 | ANSWERED | doc/active/248-MKT-2-same-game-articles-linking.md
248 | 248-MKT-3a-display-matrix | doc/active |  |  | 248-MKT-3a: subtype × 表示先 matrix | HOLD | user回答: マーケ拡張は後回し。 | 246後 | ANSWERED | doc/active/248-MKT-3a-display-matrix.md
250 | 250-QA-1 | doc/active | READY | P0(user 手直し負担軽減、即効) | manager / coach / player_comment 系で quote_count=0 の本文生成を止めて review 倒し | KEEP | ??????/strict????????postgame strict?farm_result?lineup?quote? | ??????????? | ANSWERED | doc/active/250-QA-1-manager-quote-zero-review.md
250 | 250-QA-3 | doc/active | READY | P0(user 手直し負担軽減、即効) | fetcher 側 weak generated title review 倒し(PHP weak_title 同等の Python 移植 + narrow phrase list) | KEEP | ??????/strict????????postgame strict?farm_result?lineup?quote? | ??????????? | ANSWERED | doc/active/250-QA-3-fetcher-weak-title-review.md
254 | 254-QA | doc/active | READY | P1 | 投手回数表記揺れ正規化 helper(`6` / `6.0` / `6回1/3` / `6.1` / `6回2/3` 統一) | KEEP | ???????????????????? | ??/????????? | ANSWERED | doc/active/254-QA-starter-innings-normalization.md
275 | 275-QA-github-actions-tests-failed-regression-audit | doc/active | AUDIT_DONE / READY_FOR_FIX | P1 (P0 公開復旧 観察継続中、P0 再発時はそちら最優先) | 275-QA-github-actions-tests-failed-regression-audit | ABSORB/DONE???299 | GitHub Actions??????????CI???299?????? | CI????close?? | ANSWERED | doc/active/275-QA-github-actions-tests-failed-regression-audit.md
277 | 277-QA-title-player-name-backfill | doc/active | REVIEW_NEEDED | P1 (品質改善 series 1/4、最優先) | 277-QA-title-player-name-backfill | KEEP/?????? | ???????????????????????????????SEO??? | ????clarity-first??? | ANSWERED | doc/active/277-QA-title-player-name-backfill.md
278 | 278-QA-rt-title-cleanup | doc/active | READY_FOR_FIX | P2 (品質改善 series 3/4) | 278-QA-rt-title-cleanup | KEEP/?????? | ???????????????????????????????SEO??? | ????clarity-first??? | ANSWERED | doc/active/278-QA-rt-title-cleanup.md
279 | 279-QA-mail-subject-clarity | doc/active | READY_FOR_FIX | P1 (品質改善 series 2/4) | 279-QA-mail-subject-clarity | KEEP/?????? | ???????????????????????????????SEO??? | ????clarity-first??? | ANSWERED | doc/active/279-QA-mail-subject-clarity.md
280 | 280-QA-summary-excerpt-cleanup | doc/active | READY_FOR_FIX | P2 (品質改善 series 4/4) | 280-QA-summary-excerpt-cleanup | KEEP/?????? | ???????????????????????????????SEO??? | ????clarity-first??? | ANSWERED | doc/active/280-QA-summary-excerpt-cleanup.md
281 | 281-QA-farm-result-backlog-allowlist | doc/active | REVIEW_NEEDED | P1 (昼帯コンテンツ充実) | 281-QA-farm-result-backlog-allowlist | KEEP | ?????????????????????????? | ??/????????? | ANSWERED | doc/active/281-QA-farm-result-backlog-allowlist.md
282 | 282-COST-gemini-preflight-article-gate | doc/active | REVIEW_NEEDED | P1 (cost 削減) | 282-COST-gemini-preflight-article-gate | HOLD/?? | Gemini preflight gate?????flag ON?????? | 293 FULL_EXERCISE_OK???? | ANSWERED | doc/active/282-COST-gemini-preflight-article-gate.md
289 | 289-OBSERVE-post-gen-validate-mail-notification | doc/active | REVIEW_NEEDED | **P0 equivalent**(silent skip = user 受け入れ NG) | 289-OBSERVE-post-gen-validate-mail-notification | KEEP/BUG-004親候補 | post_gen_validate通知・silent skip可視化。BUG-004と関連。 | BUG-004へ関連付け | NO | doc/active/289-OBSERVE-post-gen-validate-mail-notification.md
290 | 290-QA-weak-title-rescue-backfill | doc/active | REVIEW_NEEDED | P1(289 で見えた A/B 群を publish/review に戻す) | 290-QA-weak-title-rescue-backfill | KEEP | weak title rescue??????????? | title clarity???? | ANSWERED | doc/active/290-QA-weak-title-rescue-backfill.md
293 | 293-COST-preflight-skip-visible-notification | doc/active | DESIGN_DRAFTED(実装 hold、user 判断後 impl 起票) | P1(282-COST flag ON 前提条件、cost 削減と silent skip 防止のバランス) | 293-COST-preflight-skip-visible-notification | KEEP/OBSERVE | preflight skip visible???282??? | ?exercise evidence??? | ANSWERED | doc/active/293-COST-preflight-skip-visible-notification.md
297 | 297-OPS-pause-codex-shadow-until-redesign | doc/active | READY_FOR_EXEC(user 明示 GO 済、Codex便で execute) | P1(現状リスク即時遮断、defensive) | 297-OPS-pause-codex-shadow-until-redesign | DONE候補 | user回答: codex-shadow-triggerは止めた。read-onlyでpause確認できればclose候補。 | scheduler pause確認 | ANSWERED | doc/active/297-OPS-pause-codex-shadow-until-redesign.md
095 | 095-E-wsl-cron-reboot-resilience | doc/waiting | READY(現状の WSL2 systemd 設定で auto-start 期待、reboot 検証は user op) | P2(095-D 完了後、095 cron 安定化の補完) | 095-E WSL cron reboot resilience | HOLD/低優先 | WSL cron resilience。GCP移行後は優先低。 | 必要時のみ | NO | doc/waiting/095-E-wsl-cron-reboot-resilience.md
155 | 155-gcp-cron-migration | doc/waiting | **IN_FLIGHT**(Phase 1a `88391d0` / 1b `c5adfa3` done、Phase 2 = ChatGPT phasing 168-175 chain で展開中) | P0.5(速報掲示板 24/7 化、PC sleep 依存解消) | 155 gcp-cron-migration(WSL cron → Cloud Run Jobs 移行) | OBSOLETE候補 | GCP cron migrationは既に移行済みの可能性高い。 | 現状と照合 | YES | doc/waiting/155-gcp-cron-migration.md
195 | 195-article-footer-manual-x-share-corner | doc/waiting | READY_FOR_AUTH_EXECUTOR | P0.5 | 195 article footer 手動 X 投稿シェアコーナー(B1) | KEEP | user回答: 記事下の手動Xシェア導線は完全にはできていない。 | 246/marketing laneとは別にfront確認 | ANSWERED | doc/waiting/195-article-footer-manual-x-share-corner.md
197 | 197-195-live-deploy | doc/waiting | READY_FOR_AUTH_EXECUTOR | P0.5 | 197 / 195 article footer X share corner live deploy(canary disabled start) | KEEP | user回答: 195が完全ではないためlive deploy/残作業確認が必要。 | 195とセットで確認 | ANSWERED | doc/waiting/197-195-live-deploy.md
201 | 201-readiness-guard-test-time-dependent-flaky | doc/waiting | **READY** | P1 | 201 readiness-guard test time-dependent flaky | ABSORB?299 | pytest/flaky??????201?299??????? | 299??? | ANSWERED | doc/waiting/201-readiness-guard-test-time-dependent-flaky.md
205 | 205-gcp-runtime-drift-audit | doc/waiting | WAITING | P0.5 | 205 GCP runtime drift audit | HOLD/ABSORB | runtime drift audit。230/opsへ吸収。 | 必要時 | NO | doc/waiting/205-gcp-runtime-drift-audit.md
210 | 210-primary-source-expansion-plan | doc/waiting | REVIEW_NEEDED | P0.5 | 210 primary source expansion plan(doc-only spec) | ABSORB?288 | source expansion??288????OK? | 288????????? | ANSWERED | doc/waiting/210-primary-source-expansion-plan.md
210 | 210b-rss-sources-config-additions | doc/waiting | REVIEW_NEEDED | P0.5 | 210b RSS source config additions(repo-only audit) | ABSORB?288 | source expansion??288????OK? | 288????????? | ANSWERED | doc/waiting/210b-rss-sources-config-additions.md
210 | 210e-youtube-video-source-coverage-audit | doc/waiting | REVIEW_NEEDED | P1 | 210e YouTube / 公式動画 source coverage audit | ABSORB?288 | source expansion??288????OK? | 288????????? | ANSWERED | doc/waiting/210e-youtube-video-source-coverage-audit.md
230 | 230-gcp-cost-governor-and-runtime-spend-reduction | doc/waiting | REVIEW_NEEDED | P0.5 | 230 GCP cost governor + runtime spend reduction | HOLD | GCP runtime cost???????????????? | ??? | ANSWERED | doc/waiting/230-gcp-cost-governor-and-runtime-spend-reduction.md
230 | 230A-gcp-runtime-cost-governor-plan | doc/waiting | REVIEW_NEEDED | P0.5 | 230-A GCP runtime cost governor 具体提案 | HOLD | GCP runtime cost???????????????? | ??? | ANSWERED | doc/waiting/230A-gcp-runtime-cost-governor-plan.md
230 | 230A1-scheduler-cadence-phase1-runbook | doc/waiting | REVIEW_NEEDED | P0.5 | 230-A1 scheduler cadence governor phase 1 runbook | HOLD | GCP runtime cost???????????????? | ??? | ANSWERED | doc/waiting/230A1-scheduler-cadence-phase1-runbook.md
230 | 230D-scheduler-overlap-audit | doc/waiting | REVIEW_NEEDED | P0.5 | 230-D scheduler overlap audit | HOLD | GCP runtime cost???????????????? | ??? | ANSWERED | doc/waiting/230D-scheduler-overlap-audit.md
234 | 234-impl-7 | doc/waiting | READY_FOR_AUTH_EXECUTOR | P1 | 234 contract 反映(probable_starter / pregame の本文 hardening) | KEEP | ??????/strict????????postgame strict?farm_result?lineup?quote? | ??????????? | ANSWERED | doc/waiting/234-impl-7-probable-starter-pregame-body-hardening.md
238 | 238-night-draft-only-and-morning-decision-report | doc/waiting | WAITING | P0.5 | 238 night-draft-only mode + morning decision report | OBSOLETE?? | ??draft-only / ?????????? | obsolete?? | ANSWERED | doc/waiting/238-night-draft-only-and-morning-decision-report.md
246 | 246-MKT-today-giants-fan-guide | doc/waiting | HOLD | P0.5 | 246-MKT today giants fan guide | KEEP | user回答: 今日の巨人ファン観戦ガイドはやりたい。 | MKT本線として保持 | ANSWERED | doc/waiting/246-MKT-today-giants-fan-guide.md
249 | 249-INGEST-live-game-ingestion-expansion | doc/waiting | HOLD | P1 | 249-INGEST live game ingestion expansion | HOLD | 試合中ingestion強化。Cloud Run/Scheduler影響大。 | user GOまで保持 | NO | doc/waiting/249-INGEST-live-game-ingestion-expansion.md
251 | 251-SEO | doc/waiting | HOLD | P2 | default noindex からの部分 index 解放戦略(後段相談、HOLD) | DONE/OBSOLETE候補 | user回答: SEOはいじらない、もうできている。 | ACTIVEに上げない | ANSWERED | doc/waiting/251-SEO-noindex-release-strategy.md
252 | 252-QA | doc/waiting | BACKLOG | P2 | X 投稿候補 path 単独 fact check 追加(現状 publish_notice_email_sender 経由のみ、x_post_generator 単独経路の薄い穴を埋める narrow) | OBSOLETE候補 | user回答: 不要。XはGPTs手動運用へ寄せたため優先度低。 | obsolete候補へ | ANSWERED | doc/waiting/252-QA-X-fact-check-backlog.md
253 | 253-QA | doc/waiting | NOT_NOW | P3 | mail summary 内 source 断片の fact contains check(現状 truncation のみ、実例待ち) | HOLD/低優先 | mail summary fact checkは通知本文品質。P3。 | 必要時だけ | NO | doc/waiting/253-QA-mail-summary-fact-check-backlog.md
255 | 255-MKT-fan-guide-expansion-and-comment-badge | doc/waiting | HOLD | P1 | 255-MKT fan guide expansion and comment badge | HOLD | user回答: コメントbadge等は後回し。 | 246後 | ANSWERED | doc/waiting/255-MKT-fan-guide-expansion-and-comment-badge.md
256 | 256-QA-manager-player-quote-strict-subset | doc/waiting | HOLD | P0.5 | 256-QA manager/player quote strict subset | KEEP | ??????/strict????????postgame strict?farm_result?lineup?quote? | ??????????? | ANSWERED | doc/waiting/256-QA-manager-player-quote-strict-subset.md
260 | 260-MKT-fan-original-article-types-and-templates | doc/waiting | HOLD_DESIGN | P2 (design only、実装しない) | 巨人ファン向け独自記事型・テンプレ設計 | HOLD_DESIGN | user回答: 独自記事型は後回し。 | 設計保持のみ | ANSWERED | doc/waiting/260-MKT-fan-original-article-types-and-templates.md
264 | 264-QA-cleanup-existing-duplicates | doc/waiting | DESIGN_DRAFTED + HOLD(cleanup mutation HOLD) | **P2**(read-only audit のみ即可、cleanup mutation は user 明示 GO 必須) | 264-QA-cleanup-existing-duplicates | ABSORB/?????? | ??cleanup????????????????? | 229/235/300/BUG-004??? | ANSWERED | doc/waiting/264-QA-cleanup-existing-duplicates.md
274 | 274-OPS-mail-filter-github-actions-noise | doc/waiting | READY_FOR_USER_APPLY | P2 (受信トレイ整理、本番影響なし) | 274-OPS-mail-filter-github-actions-noise | OBSOLETE候補 | user回答: 不要。GmailフィルタでありCI赤の根本対応ではない。 | obsolete候補へ | ANSWERED | doc/waiting/274-OPS-mail-filter-github-actions-noise.md
283 | 283-MKT-unique-article-requirements-and-regression-contract | doc/waiting | DESIGN_ONLY (実装なし、要件定義のみ) | P1 (個性的記事の土台、既存テンプレ崩さず定義) | 283-MKT-unique-article-requirements-and-regression-contract | KEEP | ??????/regression contract???? | ??/??????? | ANSWERED | doc/waiting/283-MKT-unique-article-requirements-and-regression-contract.md
288 | 288-INGEST-source-coverage-expansion | doc/waiting | DESIGN_DRAFTED + HOLD | P2(289 安定後、source 拡張) | 288-INGEST-source-coverage-expansion | HOLD | user回答: source追加・取得元拡張は後で。 | source追加はuser GOまでHOLD | ANSWERED | doc/waiting/288-INGEST-source-coverage-expansion.md
291 | 291-OBSERVE-candidate-terminal-outcome-contract | doc/waiting | DESIGN_DRAFTED(実装 hold、289 完遂後 user 判断) | P0 equivalent(silent skip 再発防止の契約) | 291-OBSERVE-candidate-terminal-outcome-contract | ACTIVE??/BUG-004+ | ???=publish?????publishable??OK???????review/hold/???????????????? | BUG-004?????read-only audit | ANSWERED | doc/waiting/291-OBSERVE-candidate-terminal-outcome-contract.md
292 | 292-OBSERVE-body-contract-fail-notification | doc/waiting | DESIGN_DRAFTED(実装 hold、289 完遂後 user 判断) | P0 equivalent(silent skip 第 2 経路) | 292-OBSERVE-body-contract-fail-notification | ABSORB/ledger-only | body_contract fail?????????ledger/log???????????? | BUG-004??????????????? | ANSWERED | doc/waiting/292-OBSERVE-body-contract-fail-notification.md
294 | 294-PROCESS-release-composition-gate | doc/waiting | DESIGN_DRAFTED | P1(release management、HOLD ticket 暗黙 carry 再発防止) | 294-PROCESS-release-composition-gate | KEEP/親ticket | release composition gate。BUG-005/006/007/009の吸収先。 | 統合親にする | NO | doc/waiting/294-PROCESS-release-composition-gate.md
295 | 295-QA-subtype-evaluator-misclassify-fix | doc/waiting | DESIGN_DRAFTED + HOLD(289 安定 + 290 整理後 user 判断) | P1(silent 候補消失の主因の 1 つ、2-3 件/trigger) | 295-QA-subtype-evaluator-misclassify-fix | KEEP/P1?? | subtype??????????????????comment??postgame???????????????????fact???? | 295???234/247?????guard?? | ANSWERED | doc/waiting/295-QA-subtype-evaluator-misclassify-fix.md
296 | 296-OBSERVE-codex-shadow-role-redesign | doc/waiting | DESIGN_DRAFTED + HOLD | P1(GCP Codex 役割明確化、現状観察不能で危険) | 296-OBSERVE-codex-shadow-role-redesign | OBSOLETE候補 | user回答: codex-shadow再設計はいらない。 | 297 pause確認後、再設計はobsolete候補 | ANSWERED | doc/waiting/296-OBSERVE-codex-shadow-role-redesign.md
| HALLUC-LANE-002-llm-based-fact-check-augmentation | doc/waiting | **doc-first 起票のみ**(実装 fire は user 明示 trigger 後、Gemini API 課金 = CLAUDE.md §11 user judgment 8 類型該当) | P1(PUB-004 安定運用後の品質強化レーン、PUB-004 の前提**ではない**) | HALLUC-LANE-002 LLM-based fact-check augmentation | 要確認 | 個別確認が必要。 | 棚卸し継続 | NO | doc/waiting/HALLUC-LANE-002-llm-based-fact-check-augmentation.md
| PUB-004-D-all-eligible-draft-backlog-publish-ramp | doc/waiting | READY(PUB-004-B `f451f17` land 後の主線) | **P0.5** | PUB-004-D all-eligible-draft-backlog-publish-ramp | 要確認 | 個別確認が必要。 | 棚卸し継続 | NO | doc/waiting/PUB-004-D-all-eligible-draft-backlog-publish-ramp.md
299 | 299-QA-flaky-transient-baseline | docs/ops | OBSERVE | P1 | flaky/transient/pytest baseline?? | KEEP? | pytest/CI/flaky??????201/275??????? | CI baseline?????close????? | ANSWERED | docs/ops/OPS_BOARD.yaml

## 02_Consolidation
親/分類 | 吸収候補 | 理由 | 扱い
294-PROCESS | BUG-005 / BUG-006 / BUG-007 / BUG-009 | deploy混入・dirty・rollbackはrelease hygieneで一体管理 | 統合
293-COST / 229 | BUG-010〜014 | Gemini費用雪崩・cache・prompt/capはcost governorで一体管理 | 統合
BUG-004 / 289 / 291 / 292 | silent skip / 候補消失 | userに見えない終端状態をまとめて見る | 統合
234 / 247 / 277〜280 | 本文・タイトル・summary品質 | 品質系が分散。親を決めて吸収 | 統合候補
246-MKT | 248-MKT-* / 255-MKT / 260-MKT | マーケ導線・観戦ガイド・独自記事型を分けすぎない | 統合候補
X/GPTs手動方針 | 252 / MKT系X候補 | X自動化しないため低優先 | HOLD/OBSOLETE候補

## 03_CloseCandidates
candidate | proposed | close check
240 | DONE維持 | 完了済み。履歴だけ。
245 | DONE候補 | frontに自動投稿が出なければclose。
297 | DONE候補 | codex-shadow-trigger pause済みならclose。
195/197 | DONE候補 | 記事下Xシェア導線がliveならclose。
274 | OBSOLETE候補 | Gmail filter。CI根本対応ではない。
252 | OBSOLETE候補 | GPTs手動運用で優先低。

## 04_Hearing
優先 | 聞きたいこと | なぜ必要か | user回答形式 | user回答 | 反映案
1 | 245: 画面上に「自動投稿」カテゴリはまだ見えるか | 見えなければDONE候補にできる | 見える / 見えない / 不明 | 見える | 245はDONE不可。front表示修正としてKEEP/次候補。
2 | 297: codex-shadow-trigger はもう止めた前提でよいか | pause済みならDONE候補にできる | 止めたはず / 不明 | 止めた | 297はread-onlyでpause確認できればDONE候補。
3 | 252/274 は不要寄りとしてOBSOLETE候補でよいか | X手動GPTs・Gmail filterで優先度が低い | OK / HOLD | 不要 | 252/274はOBSOLETE候補。
4 | 275: GitHub Actions赤は今も気にするか | 赤ならKEEP、緑ならDONE候補 | 気にする / 後で / 不明 | エラー出てない | 275はCI緑をread-only確認できればDONE候補。
5 | 251 SEO/noindex はHOLD深めでよいか | 触るとSEO影響が大きい | OK / HOLD | HOLD深め | 251はHOLD深め。ACTIVEに上げない。

## 05_Rules
項目 | ルール
確定前提 | このExcelは棚卸し案。user確認後に反映。
ACTIVE | 最大2件。現場に一括投入しない。
OBSOLETE | 削除ではない。履歴を残して現場ACTIVEから外す。
DONE | evidenceありのみ。deploy済みだけではDONEにしない。
HOLD | 作業停止ではない。read-only/doc-only/evidenceは可。
user作業 | 最終確認のみ。ticket番号や優先度分類はしない。

## 06_Hearing_Round2
ticket/group | user回答 | 反映案
195 / 197 | 完全にはできてない | KEEP。front/manual X share導線の残作業候補。
246-MKT | やりたい | KEEP。観戦ガイド本線。
248 / 255 / 260 | 後回し | HOLD。マーケ拡張・コメントbadge・独自記事型は後段。
277 / 278 / 279 / 280 | 必要 | KEEP/統合候補。タイトル/通知/summary品質系として整理。
281 | やりたい | KEEP。二軍記事増やす系。ただしsource/公開影響に注意。
288 | 後で | HOLD。source追加は今やらない。
290 | 必要 | KEEP。weak title rescueは残す。
295 | 気になる | KEEP。subtype誤分類は残す。
296 | いらない | OBSOLETE候補。codex-shadow再設計は不要。
238 | 後で | HOLD。夜間draft-only/朝レポートは後段。
251 | SEOはいじらない。もうできてる | DONE/OBSOLETE候補。ACTIVEに上げない。

## 07_Hearing_Round3
ticket/group | user?? | ???
229 / 282 / 293 | Gemini????????????? | KEEP?????????282 flag ON?293 FULL_EXERCISE??
230 / 230A / 230A1 / 230D | ?? | HOLD?????????????
234 / 247 / 250 / 256 | ?? | KEEP???????/strict?????
254 | ?? | KEEP????????????????/?????
264 | ??cleanup??????????????? | ??cleanup????????????229/235/300/BUG-004????
283 | ?? | KEEP???????/regression contract????
291 | ????????????????????publish??????YOSHILOVER????????? | BUG-004?????P1???publish??/????/???source???audit?
292 | body_contract_validate fail?????? | ledger/log?????????????BUG-004???????????
299 / 201 / 275 | pytest/CI/flaky????? | 299??????201/275???/close???
210 / 210b / 210e | 288????OK | source expansion??288????

## 08_Hearing_Round4_5
ticket/group | user?? | ???
291 / BUG-004 | YOSHILOVER?????????????? | ???source?mail??????error????????
291 | ???????publish????????OK????PUBLISH????? | ACTIVE?read-only audit?publishable/review/hold/mail?????????
277-280 | ??????????????????????? | ???????clarty-first????????????????????
281 | ??????????????????????????? | ??/??/????YOSHILOVER???????KEEP?
247 | ??postgame????????????? | postgame strict??starter stats????fact????
250 / 256 | ??????????????????????/??/Twitter?????? | quote???????????cross-source duplicate??????
245 | ????????????????front???????? | KEEP/?front???
195 / 197 | ???X???????? | KEEP?????????????
246-MKT | ????????????????? | ???MVP????????????
BUG_INBOX | ???????Codex???ticket?????OK | user??????Codex???/???
238 | ??draft-only / ????????? | OBSOLETE???
230? | GCP runtime cost????Artifact Registry???????? | HOLD??????????????cleanup?????????
ACTIVE?? | BUG-003 / BUG-004+291?OK | ??2????

## 09_Hearing_Round6_Final
ticket/group | user?? | ???
295 subtype??? | comment??postgame???????????????????fact????????????? | KEEP?GCP?Codex repair??????????source/meta???slot-fill?numeric guard????
291 ?????? | ??????=??publish?????publishable??OK???????review/hold/???????????????? | ACTIVE BUG-004+291?read-only audit?publishable/review/hold/mail??????????
292 body_contract fail | ?????????ledger/log????????????????????? | BUG-004????????????????????
277-280 ?????? | ??????????????????SEO?????? | ????clarity-first?
?????? | CODEX_APP_TICKET_VIEW.md ? ????????_2026-05-02.xlsx ?commit OK? | ???????commit???

## 10_Cost_Principle
rule | meaning
Gemini???????????? | ????/regex/marker/source slot-fill??????
??????? | source_url_hash/content_hash/dedupe/preflight gate????
??????????source/meta?? | LLM/Codex??????????????review/????
?????????? | fail/review/hold????????????292?ledger/log???
YOSHILOVER???????? | 291????source mail??????
??????????? | SEO???????????????????

## 07_Publish0_NarrowUnlock
?? | ??
?? | BUG-004+291 ?ACTIVE?????????ticket?????
?? | publish=0??????????????????publish path????
???? | 277 title quality / 289 post_gen_validate / 290 weak title rescue?? / 4-tier strict / duplicate / backlog / freshness / body_contract / subtype??? / numeric guard / placeholder / source facts??
publish?????????? | YOSHILOVER???source_url???subtype/template_key high confidence?numeric guard pass?body_contract pass?placeholder???silent skip???title???????????????review/hold????
?????? | publish gate??????????????????????noindex???review threshold???????mail???user?????SEO??
??Claude????? | BUG-004+291 ??? publish=0???? + narrow publish-path unlock ????????????ticket????read-only?????????????????????publish path?????????????

## 08_2026_05_03_PMO
?? | ??
ACTIVE | BUG-004+291 publish=0???? + narrow publish-path unlock ?1??292 body_contract_fail durable ledger????????????????
OBSERVE | 282-COST flag ON??preflight active rejection?? / 298 5/3 19:35 JST 24h gate??????????
USER_DECISION_REQUIRED | 245 WP plugin upload???
??? | 277/279/278/280 title/mail/summary??234/247/250/256/254/295 ???????subtype??246-MKT/195/197/281 ????????????230/288/251/252/274/296/238 HOLD/OBSOLETE???
?? | ??????????????????292??ACTIVE??publish gate?????postgame strict/stale/duplicate??????noindex???review threshold?????mail???body_contract_fail??????????
?? | ????????????????publish path????
publish???? | YOSHILOVER???source_url???subtype/template_key high confidence?numeric guard pass?body_contract pass?placeholder???silent skip???title???????????????review/hold?????
??Claude???? | ??Claude?BUG-004+291????????????publish=0????+narrow publish-path unlock?BUG-004+291???????????????????292 body_contract_fail durable ledger?????ACTIVE?????????????????????????????????read-only?publish=0??????????unlock???????????????????